LURE

Phishing Analysis & IOC Extraction Platform

Detailed Implementation Plan

Fevra Security Portfolio  ·  February 2026

| Project | Lure — Phishing Analysis Platform |
| --- | --- |
| Version Target | v1.0.0 |
| Total Phases | 5 Phases over 10 Weeks |
| Primary Language | Python 3.11+ |
| Document Status | Implementation-Ready |

# Contents

# Executive Summary

Lure is a command-line and API-driven phishing analysis platform purpose-built for L1/L2 SOC analysts. Its core value proposition is compressing the 15–45 minute manual email triage workflow into a sub-90-second automated analysis with a complete, structured verdict report.

The platform ingests .eml and .msg files, orchestrates six analysis modules across a fully async pipeline, and produces output in JSON, HTML, STIX 2.1, and direct integrations with TheHive, Cortex, and MISP.

## Design Philosophy

Every click a Tier-1 analyst makes on a suspicious email should be replaceable by a single Lure command. This is not a research tool — it is an operational platform with zero tolerance for crashes, undefined behavior on malformed inputs, or API failures that block a triage workflow.

Core Principle Lure is analyst-first. Every design decision — async enrichment, graceful API degradation, cached results, one-command invocation — exists to reduce analyst cognitive load and time-to-verdict during a live incident.

## Scope: What Lure v1.0 Covers

| Capability | Coverage | Notes |
| --- | --- | --- |
| Email ingestion | .eml and .msg files | RFC 5322 + OLE Compound format |
| Header forensics | SPF · DKIM · DMARC · Received chain · Reply-To | Full authentication validation |
| IOC extraction | URLs · IPs · Domains · Hashes · Emails · Wallets | Defanged + encoded variants |
| Attachment scanning | YARA + static detonation signals | VBA macros · PDF elements · Office |
| Threat enrichment | VT · AbuseIPDB · Shodan · urlscan.io · OTX | Cached · async · gracefully degraded |
| Risk scoring | Weighted signal engine → 4-tier verdict | Configurable weights via YAML |
| Output formats | JSON · HTML · STIX 2.1 · TheHive · MISP | SARIF planned for v1.1 |
| LLM analysis | Verdict explanation via local Ollama | qwen2.5:7b · opt-in |
| Campaign correlation | Jaccard similarity across email set | SQLite persistence |
| MCP server | Expose analysis functions as MCP tools | Claude Code integration |

# Architecture

Lure is structured as a pipeline of six independent, composable modules orchestrated by a central Pipeline class. Each module can run standalone (for testing) or as a stage in the full pipeline. The async enrichment layer is the performance-critical path — all API calls run concurrently with per-API rate-limit semaphores.

## Repository Structure

lure/

├── lure/

│ ├── __init__.py

│ ├── cli.py # Typer CLI entrypoint

│ ├── pipeline.py # Orchestrates all modules

│ ├── config.py # Settings via Pydantic + .env

│ ├── models.py # Pydantic data models (shared types)

│ ├── cache.py # SQLite TTL cache for enrichment

│ ├── modules/

│ │ ├── parser.py # A: Email parsing + header forensics

│ │ ├── extractor.py # B: IOC extraction (all surfaces)

│ │ ├── scanner.py # C: YARA scanning engine

│ │ ├── enricher.py # D: Async enrichment orchestrator

│ │ ├── scorer.py # E: Risk scoring + verdict engine

│ │ └── reporter.py # F: Output formatting

│ ├── enrichers/

│ │ ├── virustotal.py # VT API v3 client

│ │ ├── abuseipdb.py # AbuseIPDB v2 client

│ │ ├── shodan.py # Shodan API client

│ │ ├── urlscan.py # urlscan.io async client

│ │ ├── otx.py # AlienVault OTX client

│ │ ├── urlhaus.py # URLhaus feed client

│ │ └── whois.py # WHOIS + domain age

│ ├── llm/

│ │ ├── ollama_client.py # Ollama API wrapper

│ │ └── prompts.py # Structured prompts + Pydantic models

│ ├── integrations/

│ │ ├── thehive.py # TheHive4py wrapper

│ │ ├── misp.py # PyMISP wrapper

│ │ └── stix_builder.py # STIX 2.1 bundle builder

│ ├── mcp/

│ │ └── server.py # MCP server exposing Lure as tools

│ └── templates/

│ ├── report.html.j2 # Jinja2 HTML report template

│ └── summary.txt.j2 # Terminal summary template

├── rules/

│ ├── phishing/ # Phishing kit YARA rules

│ ├── malware/ # Malware family rules

│ ├── documents/ # Office + PDF rules

│ └── custom/ # Analyst-generated rules (--learn)

├── tests/

│ ├── samples/ # Test .eml files (safe)

│ ├── test_parser.py

│ ├── test_extractor.py

│ ├── test_scanner.py

│ └── test_scorer.py

├── .env.example # API key template

├── pyproject.toml

└── README.md

## Pipeline Data Flow

All inter-module data flows through typed Pydantic models. The pipeline is a sequential async chain where each module receives the cumulative analysis state and adds its findings to it.

| Stage | Module | Input | Output Added | Async? |
| --- | --- | --- | --- | --- |
| 1 | parser.py | File path (.eml / .msg) | HeaderAnalysis, raw MIME parts | No |
| 2 | extractor.py | MIME parts, body text, attachments | IOCSet (all types, deduplicated) | No |
| 3 | scanner.py | Attachment bytes, MIME parts | YARAMatchSet | No |
| 4 | enricher.py | IOCSet | EnrichmentResult (all APIs) | Yes — concurrent |
| 5 | scorer.py | HeaderAnalysis + IOCSet + YARAMatchSet + EnrichmentResult | RiskScore, Verdict, SignalsFired | No |
| 6 | reporter.py | Full AnalysisResult | JSON / HTML / STIX / TheHive / MISP | Partial |

## Core Data Models (models.py)

All data flowing through the pipeline is typed with Pydantic v2. This provides automatic validation, serialization to JSON, and IDE autocomplete throughout the codebase.

| Model | Key Fields | Notes |
| --- | --- | --- |
| EmailFile | path, file_type (eml/msg), sha256 | Input model — validated on ingest |
| HeaderAnalysis | from_addr, reply_to, spf, dkim, dmarc, originating_ip, received_hops, anomalies | Output of parser.py |
| IOCSet | ips, domains, urls, hashes, emails, wallets (all typed lists) | Deduplicated across all extraction sources |
| YARAMatch | rule_name, ruleset, attachment_name, strings_matched, offset | One per match — list in YARAMatchSet |
| AttachmentAnalysis | filename, mime_type, sha256, vba_macros, pdf_elements, yara_matches | Per-attachment static analysis |
| EnrichmentResult | virustotal, abuseipdb, shodan, urlscan, otx, whois (dicts keyed by IOC) | Keyed by indicator value |
| RiskScore | total_score, signals_fired (list[Signal]), verdict, verdict_color | Output of scorer.py |
| AnalysisResult | All of the above + analyst_summary, analysis_timestamp, email_hash | Root output model — serialized to JSON |

# Implementation Phases

Lure is built in five sequential phases over ten weeks. Each phase ends with a working, testable deliverable. Do not begin the next phase until the current phase has passing tests and a demo-ready CLI invocation.

| Phase | Name | Duration | End-of-Phase Deliverable |
| --- | --- | --- | --- |
| 1 | Foundation & Email Parser | Weeks 1–2 | lure analyze email.eml → structured header output + IOC list |
| 2 | YARA Scanner + Attachment Analysis | Weeks 3–4 | lure analyze email.eml → header + IOCs + YARA matches |
| 3 | Enrichment API Layer | Weeks 5–6 | lure analyze email.eml → full enriched report in JSON + HTML |
| 4 | Scoring Engine + SOC Integration | Weeks 7–8 | lure analyze email.eml → verdict + TheHive case + MISP event |
| 5 | LLM Layer + MCP Server + Polish | Weeks 9–10 | lure analyze email.eml → complete report with AI summary + MCP tools |

| PHASE 1 Weeks 1–2 Foundation, Email Parser & IOC Extractor |
| --- |
| Objective: Establish project scaffolding and build the two most foundational modules: the email parser (header forensics) and the IOC extractor. End state: a working CLI that ingests an .eml or .msg file and outputs a structured JSON with all headers validated and all IOCs extracted. |
| ▸ | Set up project with pyproject.toml, Pydantic v2 models, Typer CLI, python-dotenv config |
| ▸ | Implement EmailFile ingestion — handle .eml (mail-parser) and .msg (extract-msg) with file type detection via python-magic |
| ▸ | Build HeaderAnalysis module: SPF (pyspf), DKIM (dkimpy), DMARC (checkdmarc), Received chain walking |
| ▸ | Implement Reply-To mismatch detection, X-Originating-IP extraction, X-Mailer parsing |
| ▸ | Build IOCExtractor: run iocextract + iocsearcher over body and all MIME parts; BeautifulSoup for HTML href/src extraction |
| ▸ | Add attachment extraction layer: pdfplumber for PDFs, python-docx for Word, oletools for Office |
| ▸ | Implement homograph detection via unicodedata + tldextract punycode handling |
| ▸ | Implement multi-hop redirect chain following (requests, depth-limited to 5 hops) |
| ▸ | Write pytest suite: 10+ test .eml files covering SPF pass/fail, DKIM variants, defanged IOCs |
| ▸ | CLI: lure analyze <file> → prints JSON to stdout; --output flag for file; --format flag for json/text |

### Phase 1 Module Specifications

| Module | Email Parser |
| --- | --- |
| File | lure/modules/parser.py |
| Description | Parses .eml and .msg email files into a structured HeaderAnalysis model. Performs SPF, DKIM, and DMARC validation. Walks the Received chain to find the true originating IP. Flags routing anomalies. |
| Inputs | .eml or .msg file path (str) |
| Outputs | HeaderAnalysis Pydantic model |
| Key Dependencies | mail-parser, extract-msg, pyspf, dkimpy, checkdmarc, dnspython |
| Critical Pitfall | Never trust Authentication-Results headers added by relay servers. Only consume the topmost header added by the final receiving MTA. Validate this by checking the first Received header's "by" hostname matches your expected mail gateway. |

| Module | IOC Extractor |
| --- | --- |
| File | lure/modules/extractor.py |
| Description | Extracts and deduplicates all IOCs from email body (plain text + HTML), headers, and all MIME part attachments. Runs defanging/refanging on all extracted values before deduplication. Validates extracted domains against IANA public suffix list. |
| Inputs | List of MIME parts (body, attachments) as strings/bytes |
| Outputs | IOCSet Pydantic model (all types deduplicated) |
| Key Dependencies | iocextract, iocsearcher, beautifulsoup4, pdfplumber, python-docx, oletools, urlextract, tldextract |
| Critical Pitfall | The anchor text trap: always extract from href/src attributes (BeautifulSoup), not rendered HTML text. The visible link and the actual destination are different in every credential phishing email. |

| PHASE 2 Weeks 3–4 YARA Scanner & Attachment Static Analysis |
| --- |
| Objective: Build the YARA scanning engine and static attachment detonation module. End state: Lure produces attachment analysis with YARA matches, VBA macro extraction, and PDF element scoring for every email. |
| ▸ | Download and structure YARA rule sets: signature-base, InQuest/yara-rules, reversinglabs, PhishingKitHunter |
| ▸ | Implement rule compiler: compile all .yar files from rules/ directory at startup, cache compiled object |
| ▸ | Build yaramail-based scan orchestrator: scan headers, body, normalized body, each attachment separately |
| ▸ | Implement archive decompressor: ZIP (stdlib), RAR (rarfile), 7z (py7zr) — recursive to depth 3 |
| ▸ | Implement file type detection by magic bytes (python-magic) before any scan or extraction |
| ▸ | Build VBA macro extractor via olevba: extract macro source, flag Shell/WScript/AutoOpen keywords |
| ▸ | Build PDF scorer via pdfid: count /JS, /OpenAction, /Launch, /EmbeddedFile, /AA elements |
| ▸ | Implement XLM macro deobfuscator via XLMMacroDeobfuscator for Excel 4.0 macros |
| ▸ | Build --learn mode: run yarGen on a confirmed sample, present generated rule to analyst for review |
| ▸ | Write pytest suite with YARA match tests using safe EICAR-style test strings |

### Phase 2 Module Specification

| Module | YARA Scanner |
| --- | --- |
| File | lure/modules/scanner.py |
| Description | Orchestrates YARA scanning of all email components using the four-part yaramail model. Decompresses archives before scanning. Detects file types by magic bytes. Runs olevba and pdfid for document-specific static analysis. |
| Inputs | List of MIME parts + attachment bytes (from parser output) |
| Outputs | YARAMatchSet + list[AttachmentAnalysis] |
| Key Dependencies | yara-python, yara-mail, python-magic, py7zr, rarfile, oletools |
| Critical Pitfall | Compile YARA rules from source .yar files at startup — never distribute compiled .yarc objects, they are platform-specific and will silently produce incorrect results on different OS/YARA version combinations. |

| PHASE 3 Weeks 5–6 Async Enrichment API Layer |
| --- |
| Objective: Build the full async enrichment orchestrator with caching, deduplication, and rate-limit management. End state: Lure enriches all extracted IOCs against all six APIs concurrently, with results cached in SQLite and full HTML report output. |
| ▸ | Build SQLite TTL cache (cache.py): keyed by api_name:indicator, configurable TTL per API (VT=48h, AbuseIPDB=24h, Shodan=72h) |
| ▸ | Build async enrichment orchestrator (enricher.py): asyncio.gather with per-API asyncio.Semaphore for rate limiting |
| ▸ | Implement VirusTotal v3 client (vt-py): files, URLs, domains, IP addresses; handle 429 with exponential backoff |
| ▸ | Implement AbuseIPDB v2 client: /check endpoint, maxAgeInDays=90, parse all response fields |
| ▸ | Implement Shodan client: host lookup, extract org/ISP/ASN/ports/vulns, Tor exit node detection |
| ▸ | Implement urlscan.io async client: POST scan → poll /result/{uuid} every 5s → parse DOM, forms, verdicts |
| ▸ | Implement AlienVault OTX client: query by IP/domain/URL/hash, parse pulse tags and malware families |
| ▸ | Implement URLhaus feed client: check URL against abuse.ch API, parse malware tags |
| ▸ | Implement WHOIS client: extract creation_date, compute domain age in days |
| ▸ | Implement Google Safe Browsing v4: batch URL lookup for phishing/malware verdict |
| ▸ | Build HTML report generator (Jinja2): color-coded verdict banner, IOC tables, enrichment badges, YARA panel |
| ▸ | Write integration tests with mocked API responses (pytest-httpx or responses library) |

### Enrichment Caching Pattern

Implementation Requirement Every enrichment API call MUST go through the cache layer. A single phishing email with 20 URLs to the same redirector domain must result in exactly 1 API call per service, not 20. Deduplication happens at the IOCSet level (Phase 1); cache lookup happens at the enricher level. Both are required.

| API | Cache TTL | Rate Limit Strategy | Semaphore Value |
| --- | --- | --- | --- |
| VirusTotal v3 | 48 hours | asyncio.Semaphore(4) per 60s window | 4 |
| AbuseIPDB v2 | 24 hours | asyncio.Semaphore(2) per 1s | 2 |
| Shodan | 72 hours | asyncio.Semaphore(1) per 1s | 1 |
| urlscan.io | 24 hours | asyncio.Semaphore(5) | 5 |
| AlienVault OTX | 24 hours | asyncio.Semaphore(10) | 10 |
| URLhaus | 6 hours | No limit (bulk API) | Unlimited |
| WHOIS | 168 hours (7d) | asyncio.Semaphore(3) | 3 |
| Google Safe Browsing | 1 hour | Batch all URLs in single request | 1 |

| PHASE 4 Weeks 7–8 Risk Scoring Engine & SOC Integrations |
| --- |
| Objective: Build the weighted signal scoring engine and all SOC integration outputs. End state: lure analyze produces a verdict with full signal breakdown, automatically creates a TheHive case with observables, and optionally submits confirmed phishing to MISP. |
| ▸ | Implement weighted signal scoring engine (scorer.py): evaluate each signal against findings, sum weights, map to verdict |
| ▸ | Implement all 17 signals: DMARC fail, YARA match, VT malicious, urlscan credential form, AbuseIPDB, SPF fail, Reply-To mismatch, homograph, DKIM fail, domain age, VT suspicious, OTX pulse, AbuseIPDB moderate, phishing keywords, URL shortener, suspicious TLD, no DMARC record |
| ▸ | Make signal weights configurable via lure/config/scoring.yaml — analysts can tune weights for their environment |
| ▸ | Implement TheHive integration: create Case, add Observable for each IOC type, trigger Cortex Analyzers |
| ▸ | Implement MISP integration: create Event, add Attributes (ip-dst, domain, url, md5, sha256, email), tag with "phishing" |
| ▸ | Build STIX 2.1 bundle builder: map IOCs to Indicator/Observable objects, produce valid STIX bundle JSON |
| ▸ | Implement campaign correlation: Jaccard similarity across all analyzed emails in SQLite, group by >0.7 threshold |
| ▸ | Build lure batch command: analyze directory of .eml files, produce campaign report |
| ▸ | Implement PDF export of HTML report via weasyprint |
| ▸ | Write end-to-end integration tests with real (safe) phishing samples from PhishTank/OpenPhish |

### Signal Weight Table

| Signal | Default Weight | Trigger Condition | Configurable? |
| --- | --- | --- | --- |
| YARA match on attachment | 4.0 | Any YARA rule fires on any MIME part | Yes |
| VT URL: any engine malicious | 3.0 | last_analysis_stats.malicious > 0 | Yes |
| DMARC fail | 2.5 | checkdmarc returns dmarc=fail | Yes |
| urlscan credential harvesting | 2.5 | Password field on non-org domain detected | Yes |
| AbuseIPDB score > 75 | 2.5 | abuseConfidenceScore > 75 | Yes |
| SPF fail | 2.0 | pyspf returns fail or hardfail | Yes |
| Reply-To mismatch | 2.0 | From domain ≠ Reply-To domain | Yes |
| Homograph domain | 2.0 | Mixed Unicode scripts in domain name | Yes |
| DKIM fail | 1.5 | dkimpy verification returns False | Yes |
| Domain age < 7 days | 1.5 | WHOIS creation_date < 7 days ago | Yes |
| VT URL: suspicious | 1.0 | last_analysis_stats.suspicious > 2 | Yes |
| OTX pulse match | 1.0 | Any OTX pulse returned for IOC | Yes |
| AbuseIPDB score 25–75 | 0.8 | abuseConfidenceScore between 25 and 75 | Yes |
| Phishing keyword in subject | 0.5 | Regex match on keyword list | Yes |
| URL shortener in body | 0.5 | Known shortener domain in URL list | Yes |
| Suspicious TLD | 0.3 | TLD in .xyz .top .click .loan .work list | Yes |
| No DMARC record | 0.3 | checkdmarc returns no DMARC record found | Yes |

| PHASE 5 Weeks 9–10 LLM Analysis Layer, MCP Server & Release |
| --- |
| Objective: Integrate the optional LLM verdict explanation layer (local Ollama) and build the MCP server that exposes Lure as a set of tools callable by Claude Code or other agents. Polish CLI, documentation, and release. |
| ▸ | Implement Ollama client (ollama_client.py): OpenAI-compatible endpoint, instructor library for structured output |
| ▸ | Build verdict explanation prompts: feed AnalysisResult JSON → request AnalystSummary (explanation, attack_scenario, recommended_actions, confidence) |
| ▸ | Build header anomaly prompts: feed Received chain → request routing anomaly analysis in structured output |
| ▸ | Implement --no-llm flag (default: skip LLM if OLLAMA_URL not set); always gracefully degrade |
| ▸ | Build MCP server (mcp/server.py) exposing: lure_analyze_email, lure_lookup_ioc, lure_get_verdict, lure_list_campaigns, lure_submit_to_misp |
| ▸ | Write MCP tool schemas with full parameter/return type documentation for agent consumption |
| ▸ | CLI polish: rich library for terminal output (progress bars, color verdict banner, tables) |
| ▸ | lure --help, lure config validate, lure rules update (pulls latest signature-base), lure cache clear |
| ▸ | Write USAGE.md, CONTRIBUTING.md, API_KEYS.md, INTEGRATIONS.md |
| ▸ | Release checklist: all tests pass, Docker image builds, MCP server starts cleanly, demo .eml files included |

# Detailed Module Specifications

## CLI Entrypoint (cli.py)

Built with Typer + Rich. Single entrypoint with subcommands.

| Command | Arguments | Description |
| --- | --- | --- |
| lure analyze <file> | --format json¦html¦stix¦all, --output <path>, --no-llm, --no-enrich | Analyze a single .eml or .msg file |
| lure batch <directory> | --format, --output-dir, --campaign-name | Analyze all .eml/.msg files in a directory |
| lure ioc <indicator> | --type ip¦url¦domain¦hash, --format json¦text | Enrich a single IOC on-demand |
| lure rules update | --ruleset all¦signature-base¦inquest¦reversinglabs | Pull latest YARA rules from GitHub |
| lure rules learn <sample> | --name <rule-name>, --ruleset custom | Generate YARA rule from confirmed sample |
| lure cache clear | --older-than <hours> | Clear enrichment cache entries |
| lure config validate |  | Validate .env, API keys, YARA rules, Ollama connection |
| lure serve mcp | --port <port> | Start MCP server for agent integration |

## Enrichment Orchestrator (enricher.py)

The enrichment orchestrator is the most performance-sensitive module. It must: deduplicate IOCs before any API calls, look up all IOCs in cache first, batch all cache misses into concurrent API calls, and write results back to cache after retrieval.

Zero-Day Window Coverage A freshly registered phishing domain will have zero VirusTotal detections for 24–72 hours. Lure MUST NOT return CLEAN based on VT alone. The zero-day window is covered by: (1) domain age from WHOIS, (2) urlscan DOM analysis revealing credential forms, (3) Google Safe Browsing, (4) PhishTank community submissions. All four must be evaluated before a CLEAN verdict is possible.

## HTML Report Template Requirements

The HTML report is what L1 analysts read during a shift. Design requirements are non-negotiable for operational use.

| Component | Requirement | Implementation |
| --- | --- | --- |
| Verdict banner | Full-width color bar (green/yellow/orange/red) with verdict text and score | CSS class on <header> element |
| SPF/DKIM/DMARC badges | Traffic-light colored pill badges (PASS=green, FAIL=red, NONE=grey) | Inline SVG or CSS badges |
| Routing chain | Text-art hop diagram: IP → Relay → Gateway with anomalies highlighted in red | Pre-formatted HTML block |
| IOC table | Sortable table: IOC value, type, enrichment badges (VT score, AbuseIPDB score) | JavaScript DataTables or CSS |
| YARA panel | Collapsible section per match: rule name, ruleset, matched strings with byte offset | Details/summary HTML |
| Attachment panel | Per-attachment: filename, type, hash, VBA/PDF findings, YARA match count | Expandable card per attachment |
| Copy IOCs button | One-click copy all IOCs as JSON to clipboard | navigator.clipboard.writeText() |
| Export PDF button | Trigger browser print dialog optimized for PDF output | window.print() + @media print CSS |
| LLM summary box | Analyst summary paragraph from LLM (highlighted, collapsible if long) | Styled blockquote element |
| Signal breakdown | Table of all signals fired with weight and trigger condition | Styled table in report body |

# Testing Strategy

Every module must have a pytest test suite that runs without real API keys. Integration tests against real APIs run separately and require keys. The goal: zero fragile tests that break because an API changed its response format.

## Test File Organization

| Test File | Coverage | Requires API Keys? |
| --- | --- | --- |
| test_parser.py | SPF/DKIM/DMARC parsing, Received chain walking, Reply-To mismatch, .msg parsing | No — uses DNS mocking |
| test_extractor.py | Defanged IOC extraction, anchor text trap, PDF URL extraction, homograph detection | No |
| test_scanner.py | YARA rule compilation, EICAR test string matching, archive decompression, VBA extraction | No |
| test_enricher.py | Cache hit/miss logic, deduplication, rate limit semaphore behavior, API response parsing | No — uses mocked HTTP |
| test_scorer.py | Each of 17 signals fires correctly, weighted sum calculation, verdict threshold mapping | No |
| test_reporter.py | JSON schema validation, HTML report structure, STIX 2.1 bundle validity | No |
| test_integration.py | Full pipeline end-to-end with real .eml samples from tests/samples/ | Optional — skipped if no keys |
| test_mcp.py | MCP tool schemas, invocation with sample inputs, structured output validation | No |

## Required Test .eml Samples

The tests/samples/ directory must include safe, non-harmful test emails covering each category. Source: PhishTank open samples, OpenPhish, and synthetically generated files.

| Filename | What It Tests | Expected Verdict |
| --- | --- | --- |
| spf_fail_dmarc_fail.eml | SPF hardfail + DMARC fail signals | SUSPICIOUS or higher |
| reply_to_mismatch.eml | From/Reply-To domain mismatch signal | SUSPICIOUS |
| yara_phishing_kit.eml | Attachment matching phishing kit YARA rule | LIKELY_PHISHING |
| vba_macro_word.eml | Word attachment with VBA AutoOpen macro | LIKELY_PHISHING |
| pdf_with_javascript.eml | PDF with /JS and /OpenAction elements | LIKELY_PHISHING |
| homograph_domain.eml | Cyrillic character in sender domain | SUSPICIOUS |
| clean_legitimate.eml | Known good email — all signals pass | CLEAN |
| defanged_iocs_body.eml | Body with hxxps:// and [.] defanged URLs | Tests extractor only |
| nested_zip_attachment.eml | ZIP containing ZIP containing exe | CONFIRMED_MALICIOUS |
| new_domain_vt_clean.eml | Day-1 phishing domain, zero VT detections | Tests zero-day coverage |

# Dependencies & Setup

## Full Dependency Installation

lure/

# Create virtual environment

python -m venv .venv && source .venv/bin/activate

# Install all Lure dependencies

pip install \

mail-parser extract-msg \

pyspf dkimpy checkdmarc dnspython \

iocextract iocsearcher ioc-fanger \

beautifulsoup4 pdfplumber python-docx "oletools[full]" \

urlextract tldextract \

yara-python yara-mail \

python-magic py7zr rarfile \

vt-py shodan OTXv2 ipwhois python-whois \

stix2 pymisp thehive4py cortex4py \

aiohttp httpx instructor ollama \

typer rich weasyprint jinja2 \

pydantic pydantic-settings python-dotenv \

pytest pytest-asyncio pytest-httpx

# Install system dependency for rarfile (macOS: brew install unar)

# sudo apt-get install unrar # Ubuntu

# Download YARA rules

git clone https://github.com/Neo23x0/signature-base rules/signature-base

git clone https://github.com/InQuest/yara-rules rules/inquest

git clone https://github.com/reversinglabs/reversinglabs-yara-rules rules/reversinglabs

## Required API Keys (.env)

| Variable | Service | Free Tier | Get Key At |
| --- | --- | --- | --- |
| VT_API_KEY | VirusTotal v3 | 4 req/min, 500/day | virustotal.com/gui/sign-in |
| ABUSEIPDB_KEY | AbuseIPDB v2 | 1,000 req/day | abuseipdb.com/account/api |
| SHODAN_API_KEY | Shodan | 100 queries/month | account.shodan.io |
| URLSCAN_KEY | urlscan.io | 1,000 private scans/day | urlscan.io/user/signup |
| OTX_KEY | AlienVault OTX | Unlimited | otx.alienvault.com |
| PHISHTANK_KEY | PhishTank | 1,000 req/day | phishtank.org/api_register |
| GSB_KEY | Google Safe Browsing v4 | 10,000 req/day | console.cloud.google.com |
| THEHIVE_URL | TheHive instance URL | Self-hosted | github.com/TheHive-Project/TheHive |
| THEHIVE_KEY | TheHive API key | Self-hosted | (TheHive admin settings) |
| MISP_URL | MISP instance URL | Self-hosted | github.com/MISP/MISP |
| MISP_KEY | MISP authkey | Self-hosted | (MISP user profile) |
| OLLAMA_URL | Local Ollama server | Free (local) | ollama.ai — bind to localhost only |

Security Note — Ollama Exposure Ollama binds to 0.0.0.0:11434 by default. Cisco Talos identified 1,100+ publicly exposed Ollama servers in September 2025. Always configure Ollama to bind only to 127.0.0.1. Set OLLAMA_HOST=127.0.0.1 in your Ollama service configuration before starting the server.

# Portfolio Positioning & Differentiation

Lure fills a genuine gap in the Fevra Security portfolio — it is the only defensive tool in the set, providing direct evidence of blue team and SOC engineering capability alongside the offensive/analysis tools.

## What Makes Lure Differentiated

| Differentiator | Most Tools Do This? | Lure's Approach |
| --- | --- | --- |
| DOM-level phishing kit detection | No — most check URL blocklists only | urlscan.io DOM analysis detects credential forms regardless of VT reputation |
| Zero-day window coverage | No — most stop at VT | Domain age + urlscan + GSB covers the 24–72h window before VT detection |
| LLM verdict explanation | No | Ollama + Instructor produces analyst-readable summary with attack scenario classification |
| Campaign correlation | No open-source tool does this | Jaccard similarity across IOC sets links related emails into campaigns |
| Static detonation without sandbox | Partial | olevba + pdfid gives 80% of sandbox signal at zero infrastructure cost |
| MCP server exposure | No security tool currently does this | Claude Code and other agents can call Lure as a tool in automated workflows |
| Configurable scoring weights | No | scoring.yaml lets each SOC team tune signal weights for their threat model |
| Graceful API degradation | Partial | Missing API keys produce warnings, not crashes — designed for key-by-key rollout |

## Resume / Portfolio Entry

Suggested Portfolio Description Lure — Phishing Analysis & IOC Extraction Platform: Built a production-grade phishing triage platform targeting L1/L2 SOC analyst workflows. Implements a six-stage async pipeline: MIME parsing with SPF/DKIM/DMARC validation, multi-surface IOC extraction with defang handling, YARA attachment scanning against Neo23x0/signature-base and InQuest/yara-rules, concurrent enrichment against VirusTotal v3, AbuseIPDB, Shodan, and urlscan.io with SQLite caching, weighted signal scoring engine with configurable 17-signal model, and output in JSON, HTML, STIX 2.1, TheHive, and MISP. Integrated local LLM (Ollama/qwen2.5) for analyst-readable verdict explanations. Exposed as MCP tools for agentic SOC automation.

# Risk Log & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| VT free tier exhausted during testing | High | Blocks enrichment development | Build cache first (Phase 3, Day 1). All tests use mocked HTTP responses. |
| YARA rule false positives from large rulesets | Medium | Low analyst trust in findings | Separate rule directories by confidence; log match rate per ruleset in tests. |
| urlscan async polling timeout on slow scans | Medium | Missing DOM analysis results | Implement configurable timeout (default 60s) with graceful skip on timeout. |
| .msg format variants break extract-msg | Low | Fails on Outlook emails | Comprehensive test suite with multiple .msg format variants; fallback to raw header extraction. |
| Ollama not installed or model not pulled | Medium | LLM features unavailable | LLM is always opt-in; --no-llm is the default if OLLAMA_URL is not set. |
| YARA compile errors from new rules in signature-base | Low | Scanner fails to start | Compile each ruleset independently; skip and log individual files that fail compilation. |
| Phishing campaign uses HTTPS on compromised legitimate domain | Medium | Domain age check fails (domain is old) | urlscan DOM analysis is the safety net — detects credential form regardless of domain history. |

# Future Roadmap — v1.1 and Beyond

| Version | Feature | Rationale |
| --- | --- | --- |
| v1.1 | SARIF output format | Compatibility with GitHub Code Scanning and VS Code security extensions |
| v1.1 | PhishDebate multi-agent LLM (two-agent debate + judge) | Better detection of subtle social engineering — published architecture (arxiv June 2025) |
| v1.1 | SMTP listener mode | Accept forwarded suspicious emails over SMTP directly into analysis pipeline |
| v1.1 | Slack/Teams alert integration | Post verdict notifications to SOC channel with one-line summary and report link |
| v1.2 | mail_to_misp direct integration | Forward confirmed phishing to MISP automatically from shared SOC mailbox |
| v1.2 | Cuckoo Sandbox integration | Submit high-scoring attachments to self-hosted Cuckoo for full behavioral analysis |
| v1.2 | EXPLICATE LIME+SHAP explainability layer | Show analyst exactly which feature values drove the verdict score — published architecture March 2025 |
| v2.0 | MultiPhishGuard five-agent LLM architecture | Text + URL + Metadata + Adversarial + Rationale agents via PPO RL — ACM CCS 2025 |
| v2.0 | Browser extension mode (Prizm integration) | In-browser analysis of suspected phishing pages, leveraging Prizm DOM scanning |
| v2.0 | Real-time CT stream monitoring | Subscribe to Certificate Transparency streams via certstream for new phishing domain detection |

Build Order Reminder Phase 1 (parser + extractor) must be complete with passing tests before Phase 2 begins. Every phase gate requires: all tests pass, lure analyze <sample.eml> produces valid output, no crashes on malformed input. Do not skip gates — a fragile enrichment layer built on a fragile parser will be unmaintainable.